## Slide 1
 | Technology |  | 
Choice of platform (product / EVM / operating systems and why | This project will use a 3rd party vendor, Mistral, to design and create System-on-a-Module boards for the DM366, DM388, and DM8127 video processing chips as well as a common carrier board that will accommodate several common interfaces and a camera module. |  | 
New technologies being developed | None |  | 
New technology risks | None |  | 
Technology comparison | This project is using established video processing chips so the technology is current but not forward-looking. The purpose is to relaunch these chips without changing them, so current technology is by design and not a limitation. |  | 
Need By Date | End/June 2016 |  | 
 | Name | Availability Date | % of time dedicated to Project
Software / Firmware | Mistral responsibility | End/June 2016 | 
Software Verification | Mistral responsibility | End/June 2016 | 
Software Validation | Mistral responsibility | End/June 2016 | 
Applications and Systems | N/A |  | 
Program Mgr | Ted George |  | 
Other key functions | Bhavin Kharadi | Bring-up Lead | Est: 2 engineers for 2 weeks full-time
<VideoVision> New product kickoff review
DM366, DM388, DM8127 SOM Modules

## Slide 2: Major Items to Close by PPR
The SOW needs to be finalized w/ Mistral
IQN consulting agreement needs to be approved
TI-supplied parts need to be ordered
‘Bring-up’ lead engineer needs to be identified and SW tests for TI bring-up need to be defined

## Slide 3: VideoVision SOM modules
This prototype development will follow the QRAS SC00098 process for HW Tools development
The Phase-I review should consider summary elements pulled from various detailed design documents:
  SOW / Project plan (preliminary)
  Functional spec (preliminary)
  Compliance targets
  Boundary agreements
Actual Phase-I deliverables
  Proposal
  Design Specification (SOW / feature XLS)

## Slide 4: SOW – Milestones / schedule
The SOW is not yet finalized with Mistral:
Milestones | Schedule |  |  | 
 | DM368 | DM388 | DM8127 | Carrier Card
Project kick off (Mistral) | T0 | T0 | T0 | T0
Specification complete | T0 + 1 | T0 + 1 | T0 + 1 | T0 + 1
High level design | T0 + 3 | T0 + 3 | T0 + 3 | T0 + 2
Schematics | T0 + 5 | T0 + 5 | T0 + 5 | T0 + 4
CAD Layout | T0 + 7 | T0 + 7 | T0 + 7 | T0 + 6
PCB | T0 + 11 | T0 + 11 | T0 + 11 | T0 + 10
Board Bringup | T0 + 12 | T0 + 12 | T0 + 12 | T0 + 11
Interface Testing | T0 + 13 | T0 + 13 | T0 + 13 | T0 + 12
Delivery | T0 + 14 | T0 + 14 | T0 + 14 | T0 + 13

## Slide 5: SOW – Estimated costs
Development Cost Element | SOM Module |  | 
 | DM368 + Carrier card | DM388 | DM8127
Design / Prototype development | $60,000 | $48,500 | $48,500
Pre-compliance test development | $7,000 | $7,000 | $7,000
Optional: respin costs | $5,000 | $5,000 | $5,000
Pre-compliance testing | $4,000 | $4,000 | $4,000
Total | $71,000 | $59,500 | $59,500
Production Cost Element | Per-Unit Cost (Estimated) |  | 
 | DM368 | DM388 | DM8127
10 Qty build | $266 | $295 | $345
100 Qty build | $98 | $128 | $144

## Slide 6: Functional spec - modules

## Slide 7: Functional spec: carrier card

## Slide 8: Compliance targets
The main TI compliance standards are the responsibility of the vendor.
  RoHS compliance
  REACH compliance
  Packaging / chemical & materials compliance
The SOW contains the standard TI language for EVM compliance requirements.
The TI team is responsible for some areas of compliance
  High voltage safety
  Power supply safety

## Slide 9: Boundary agreement from MRD (preliminary)
Number | Requirement | Reviewer’s Response
R-PLTFM-????-10 | Supports all features/functionality of IPNC DM368/DM365 RDK Product Release 5.1.0 | 
R-PLTFM-????-20 | SW performance of all key kernel benchmarks should be equal or better than existing performance numbers | 
R-PLTFM-????-30 | SW performance of all key video benchmarks should be equal or better than existing performance numbers | 
R-PLTFM-????-40 | The Operating System to be supported as part of this platform is latest Linux LTS 4.4 | N/A
R-PLTFM-????-50 | The EVM HW and SW will support the Leopard Imaging LI-CAM-AR0331 Camera Module | 
R-PLTFM-????-60 | The EVM HW and SW will support the TI WL1835MODCOM8B COM8 WiFi module |