## 1.Index
Mistral Solutions [P] Ltd.
#60 Adarsh regent,100 Feet Ring Road, Domlur Extension
Bangalore 560 071, Ph : +91-80-30912600, Fax :+91-80-25356444
TMDSCSKCC + TMDSCSK388 TEST REPORT
DELIVERY
Batch | Date | Description | Remarks
1 | 2016-08-04 | Test report for 10 Boards updated
Name of the Tester | Mistral Test Team
Board Name | TMDSCSKCC + TMDSCSK388
Contents | Sheet
Index | 1
Visual Inspection | 2
Impedance Measurement | 3
Voltage Measurement | 4
Clocks | 5
Reset | 6
Interface Test | 7

## 2. Visual Inspection
1.Visual Inspection
The preliminary tests that will be carried out on the assembled PCB’s are Check the mounted components for its correctness with regard to direction, reference no's and polarity in case of tantalum capacitors, diodes, LEDs
TMDSCSK388
2. DNI verification |  |  |  | Board Serial Number (10 Boards)
SL NO | QTY | DNI PART REFERENCE | Value | 3116CSK3880001 | 3116CSK3880002 | 3116CSK3880003 | 3116CSK3880005 | 3116CSK3880006 | 3116CSK3880007 | 3116CSK3880008 | 3116CSK3880009 | 3116CSK3880010 | 3116CSK3880012
Parts On TOP side
1 | 2 | J1 J2 | CON_3_U.FL-R-SMT | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
2 | 5 | R1 R2 R3 R37 R142 | 0E
3 | 14 | R22 R26 R31 R32 R33 R42 R43 R44 R45 R46 R56 R58 R60 R72 | 10K
Parts On BOTTOM side
1 | 1 | J5 | CON_PMC_30X2_M | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
2 | 1 | R118 | 0E
TMDSCSKCC
2. DNI verification |  |  |  | Board Serial Number (10 Boards)
SL NO | QTY | DNI PART REFERENCE | Value | 3116CSKCC0001 | 3116CSKCC0003 | 3116CSKCC0012 | 3116CSKCC0026 | 3116CSKCC0010 | 3116CSKCC0008 | 3116CSKCC0015 | 3116CSKCC0018 | 3116CSKCC0004 | 3116CSKCC0016
Parts On TOP side
1 | 1 | R19 | 4.7K | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
2 | 2 | R21 R23 | 47E
3 | 1 | R35 | 2.49K
4 | 1 | R36 | 11K
Parts On BOTTOM side
1 | 1 | C36 | 10000pF | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
2 | 1 | R90 | 4.7K
3 | 1 | R61 | 10K
4 | 1 | R88 | 0E
5 | 1 | R89 | 22E
6 | 1 | R104 | 2K

## 3.Impedance measurement
TMDSCSK388
3.Impedance Measurement | [5 empty] | Board Serial Number(10 Boards)
Sl No. | Power Supply | Probe Point | Ground | Probe Point | Expected Value | 3116CSK3880001 | 3116CSK3880002 | 3116CSK3880003 | 3116CSK3880005 | 3116CSK3880006 | 3116CSK3880007 | 3116CSK3880008 | 3116CSK3880009 | 3116CSK3880010 | 3116CSK3880012
Points on Top Side
1 | VCC_5V0 | TP4 | DGND | C43.2 |  | 10M | 10M | 82.5K | 92K | 85K | 90K | 101k | 105K | 92K | 85K
2 | PMIC_3V3 | TP13 | DGND | C43.2 |  | 6.6M | 10M | 6.6M | 4.5M | 4.65M | 10M | 2.37M | 3M | 2.5M | 2.2M
3 | VCC_3V3 | TP14 | DGND | C43.2 |  | 5.3K | 5.3K | 946E | 886E | 906E | 937E | 939E | 904E | 930E | 895E
4 | TPS_CORE_CVDD | TP3 | DGND | C43.2 |  | 318E | 308E | 295.4E | 258E | 292E | 284.7E | 273.6E | 239E | 254E | 293E
5 | TPS_CVDD_ARM | TP11 | DGND | C43.2 |  | 12.5K | 12.3K | 11.41K | 8.75K | 11.27K | 10K | 10.85K | 1.47K | 9.8K | 10.7K
6 | TPS_CVDD_HDVICP | C27.1 | DGND | C43.2 |  | 5.88K | 6K | 1.481K | 1.31K | 1.45K | 1.48K | 1.34K | 1.31K | 1.3K | 2.06K
7 | TPS_VDDA_1V8 | TP1 | DGND | C43.2 |  | 39.8K | 17.45K | 16.88K | 16.28K | 16.8K | 15.56K | 16.79K | 16.1K | 16.5K | 16.6K
8 | TPS_VDAC_1V8 | TP7 | DGND | C43.2 |  | 191K | 145.5K | 135.9K | 140K | 139.2K | 160K | 147K | 140K | 152K | 177K
9 | TPS_VHD_1V1 | TP15 | DGND | C43.2 |  | 145.5K | 146.2K | 138.3K | 139K | 140K | 133K | 135K | 134K | 145K | 138K
10 | VDD_DDR | C43.1 | DGND | C43.2 |  | 12K | 12.2K | 8.47K | 12.2K | 8.4K | 8.5K | 8.36K | 7.7K | 8.59K | 8.2K
11 | HDDAC_VREF | C46.2 | DGND | C43.2 |  | 4.88K | 4.87K | 3.273K | 3.044K | 3.276K | 3.27K | 3.268K | 3.27K | 3.2K | 3.26K
Points on BOTTOM Side
1 | VDD_DDR_VREF | C132.2 | DGND | C132.1 |  | 435K | 432K | 432K | 432K | 432K | 432K | 432K | 432K | 432K | 432K
2 | VDDR_VTT | C112.2 | DGND | C132.1 |  | 68K | 68K | 68K | 68K | 68K | 68K | 68K | 68K | 68K | 68K
TMDSCSKCC
3.Impedance Measurement | [5 empty] | Board Serial Number(10 Boards)
Sl No. | Power Supply | Probe Point | Ground | Probe Point | Expected Value | 3116CSKCC0001 | 3116CSKCC0003 | 3116CSKCC0012 | 3116CSKCC0026 | 3116CSKCC0010 | 3116CSKCC0008 | 3116CSKCC0015 | 3116CSKCC0018 | 3116CSKCC0004 | 3116CSKCC0016
Points on Top Side
1 | PMIC_3V3 | TP3 | DGND | TP1 |  | 2.1M | 5.18M | 6.6M | 5.03M | 4.3M | 5.7M | 4.18M | 6.2M | 4.73M | 5.14M
2 | VCC_3V3 | TP4 | DGND | TP1 |  | 1.7K | 940E | 946E | 921E | 910E | 936E | 933E | 900E | 930E | 890E
3 | VCCA_2V5 | TP6 | DGND | TP1 |  | 5.8K | 5.5K | 5.83K | 5.59K | 5K | 5.5K | 5.63K | 4.89K | 5.5K | 4.53K
4 | VCC_1V1 | TP8 | DGND | TP1 |  | 250E | 233E | 255.6E | 221E | 257E | 248E | 220.4E | 285E | 276E | 321E
Points on BOTTOM Side
1 | DC_VCC5V0 | C37.1 | DGND | TP1 |  | 100K | 68K | 98.6K | 95K | 100K | 110K | 95.6K | 80K | 75K | 68K
2 | VCC_CAM | C58.1 | DGND | TP1 |  | 350K | 16K | 17.02K | 16.32K | 17.04K | 16.25K | 16.7K | 16.22K | 16.4K | 16.5K
3 | VCC_1V8 | C75.2 | DGND | TP1 |  | 383.5K | 16K | 17.01K | 16K | 17K | 16.5K | 16.83K | 16.2K | 16.4K | 16.6K

## 4.Voltage measurement
TMDSCSK388
4.Voltage Measurement |  |  |  |  | Expected Voltage (V) |  |  | Board Serial Number(10 Boards)
Sl No. | Power Supply | Probe Point | Ground | Probe Point | Min | Typ | Max | 3116CSK3880001 | 3116CSK3880002 | 3116CSK3880003 | 3116CSK3880005 | 3116CSK3880006 | 3116CSK3880007 | 3116CSK3880008 | 3116CSK3880009 | 3116CSK3880010 | 3116CSK3880012
Points on Top Side
1 | TPS_VDDA_1V8 | TP1 | DGND | C43.2 | 1.71 | 1.8 | 1.89 | 1.8 | 1.813 | 1.818 | 1.81 | 1.814 | 1.814 | 1.814 | 1.813 | 1.819 | 1.809
2 | TPS_CORE_CVDD | TP3 | DGND | C43.2 | 1.14 | 1.2 | 1.26 | 1.218 | 1.216 | 1.225 | 1.228 | 1.226 | 1.224 | 1.22 | 1.224 | 1.226 | 1.227
3 | VCC_5V0 | TP4 | DGND | C43.2 | 4 | 5 | 5.5 | 4.77 | 4.82 | 4.98 | 4.96 | 4.97 | 4.96 | 4.89 | 4.96 | 4.77 | 4.88
4 | TPS_VDAC_1V8 | TP7 | DGND | C43.2 | 1.71 | 1.8 | 1.89 | 1.813 | 1.805 | 1.798 | 1.799 | 1.81 | 1.815 | 1.804 | 1.812 | 1.803 | 1.799
5 | TPS_CVDD_ARM | TP11 | DGND | C43.2 | 1.14 | 1.2 | 1.26 | 1.201 | 1.196 | 1.208 | 1.208 | 1.206 | 1.277 |  | 1.207 | 1.207 | 1.21
6 | PMIC_3V3 | TP13 | DGND | C43.2 | 3.14 | 3.3 | 3.47 | 3.263 | 3.27 | 3.282 | 3.291 | 3.276 | 3.28 | 3.27 | 3.273 | 3.259 | 3.28
7 | VCC_3V3 | TP14 | DGND | C43.2 | 3.14 | 3.3 | 3.47 | 3.292 | 3.282 | 3.289 | 3.297 | 3.28 | 3.28 | 3.27 | 3.285 | 3.296 | 3.263
8 | TPS_VHD_1V1 | TP15 | DGND | C43.2 | 1.05 | 1.1 | 1.15 | 1.104 | 1.106 | 1.104 | 1.1 | 1.112 | 1.1 | 1.107 | 1.105 | 1.105 | 1.113
9 | TPS_CVDD_HDVICP | C27.1 | DGND | C43.2 | 1.14 | 1.2 | 1.26 | 1.201 | 1.197 | 1.202 | 1.2 | 1.198 | 1.196 | 1.2 | 1.196 | 1.193 | 1.21
10 | VDD_DDR | C43.1 | DGND | C43.2 | 1.43 | 1.5 | 1.58 | 1.499 | 1.496 | 1.498 | 1.496 | 1.497 | 1.499 | 1.497 | 1.5 | 1.495 | 1.5
11 | HDDAC_VREF | C46.2 | DGND | C43.2 | 0.45 | 0.5 | 0.55 | 0.465 | 0.45 | 0.456 | 0.455 | 0.456 | 0.457 | 0.45 | 0.456 | 0.459 | 0.455
TMDSCSKCC
4.Voltage Measurement |  |  |  |  | Expected Voltage (V) |  |  | Board Serial Number(10 Boards)
Sl No. | Power Supply | Probe Point | Ground | Probe Point | Min | Typ | Max | 3116CSKCC0001 | 3116CSKCC0003 | 3116CSKCC0012 | 3116CSKCC0026 | 3116CSKCC0010 | 3116CSKCC0008 | 3116CSKCC0015 | 3116CSKCC0018 | 3116CSKCC0004 | 3116CSKCC0016
Points on Top Side
1 | VCCA_2V5 | TP6 | DGND | TP1 | 2.375 | 2.5V | 2.625 | 2.46 | 2.472 | 2.47 | 2.46 | 2.48 | 2.458 | 2.454 | 2.475 | 2.467 | 2.468
2 | VCC_1V1 | TP8 | DGND | TP1 | 1.045 | 1.1V | 1.155 | 1.09 | 1.099 | 1.102 | 1.099 | 1.1 | 1.089 | 1.09 | 1.085 | 1.092 | 1.091

## 5.Clocks
TMDSCSK388
6. Clock Measurement
Sl No. | SIGNAL NAME | Reference | Frequency | 3116CSK3880001 | 3116CSK3880002 | 3116CSK3880003 | 3116CSK3880005 | 3116CSK3880006 | 3116CSK3880007 | 3116CSK3880008 | 3116CSK3880009 | 3116CSK3880010 | 3116CSK3880012
1 | OSC32KOUT | Y1.1 | 32.768 Khz | 32.75 | 32.79 | 32.66 | 32.767 | 32.767 | 32.767 | 32.768 | 32.766 | 32.767 | 32.767
2 | DEVOSC_MXO | Y2.3 | 20 MHz | 20 | 20 | 20 | 19.99 | 19.996 | 19.99 | 19.99 | 19.99 | 19.995 | 19.996
3 | AUXOSC_MXO | Y3.3 | 27 MHz | 27.03 | 26.98 | 26.47 | 26.99 | 26.99 | 26.988 | 26.99 | 26.998 | 26.996 | 26.99
4 | CLKIN32 | U10.3 | 32.768 Khz | 32.76 | 32.77 | 32.33 | 32.768 | 32.768 | 32.768 | 36.7682 | 32.762 | 32.7681 | 32.768
5 | CLK32OUT_PMIC | R19.2 | 32.768 Khz | 31.64 | 31.5 | 32.56 | 31.915 | 32.393 | 32.645 | 31.67 | 31.8 | 32.491 | 32.504
TMDSCSKCC
6. Clock Measurement
Sl No. | SIGNAL NAME | Reference | Frequency | 3116CSKCC0001 | 3116CSKCC0003 | 3116CSKCC0012 | 3116CSKCC0026 | 3116CSKCC0010 | 3116CSKCC0008 | 3116CSKCC0015 | 3116CSKCC0018 | 3116CSKCC0004 | 3116CSKCC0016
1 | 12MHz_FT2232 | U28.3 | 12 MHz | 12 | 12.01 | 12.0002 | 12.0003 | 12.0003 | 12.0003 | 12.0003 | 12.0003 | 12.0003 | 12.0003
2 | AUD_MCLK | U15.3 | 24.576 MHz | 24.35 | 24.478 | 24.578 | 24.576 | 24.576 | 24.576 | 24.766 | 24.576 | 24.576 | 24.576

## 6.Reset
TMDSCSK388
6. Reset
Sl No. | SIGNAL NAME | REFERENCE (across where you can check TP etc) | Reset Level | 3116CSK3880001 | 3116CSK3880002 | 3116CSK3880003 | 3116CSK3880005 | 3116CSK3880006 | 3116CSK3880007 | 3116CSK3880008 | 3116CSK3880009 | 3116CSK3880010 | 3116CSK3880012
1 | nRESPWRON2 | R7.1 | 3.3V | 3.19 | 3.28 | 3.286 | 3.205 | 3.19 | 3.29 | 3.274 | 3.24 | 3.28 | 3.262
2 | CC_RST | U11.3 | 3.3V | 3.28 | 3.36 | 3.284 | 3.296 | 3.278 | 3.289 | 3.271 | 3.32 | 3.36 | 3.259
3 | DDR_PGOOD | U11.6 | 3.3V | 3.28 | 3.4 | 3.287 | 3.294 | 3.19 | 3.286 | 3.277 | 3.36 | 3.36 | 3.257
4 | DM388_PORn | U11.4 | 3.3V | 3.283 | 3.36 | 3.281 | 3.292 | 3.276 | 3.286 | 3.276 | 3.36 | 3.36 | 3.258
5 | DM388_PMIC_PWRON | SW4.4 | 5V | 4.8 | 5.2 | 4.84 | 4.98 | 4.98 | 4.87 | 4.87 | 4.96 | 4.92 | 4.81

## 7.Interface test
Note: Interface tests documented here are intended to bring-up and validate basic functionality of interfaces on the CSK TMDSCSK388 + Carrier card.
Test cases for TMDSCSKCC + TMDSCSK388 Validation
Sl No | Interface/Module Name | Test ID | Test Name |  |  | Expected Result | Test Status
[7 empty] | 3116CSKCC0001+ 3116CSK3880001 | 3116CSKCC0003+ 3116CSK3880002 | 3116CSKCC0012+ 3116CSK3880003 | 3116CSKCC0026 + 3116CSK3880005 | 3116CSKCC0010 + 3116CSK3880006 | 3116CSKCC0008 + 3116CSK3880007 | 3116CSKCC0015 + 3116CSK3880008 | 3116CSKCC0018 + 3116CSK3880009 | 3116CSKCC004+ 3116CSK3880010 | 3116CSKCC0016+ 3116CSK3880012 | #21+#13
1 | DDR3 | CSK_SW_DIAG_TEST_001 | Sequential memory read/write test | This test performs a sequential memory read/write for a fixed memory size | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary •Select test 1 in menu and check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
2 |  | CSK_SW_DIAG_TEST_002 | Random Memory Read/Write | This test performs a random memory read/write for a fixed memory size | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary •Select test 2 in menu and check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
3 |  | CSK_SW_DIAG_TEST_003 | Sequential Incremental Pattern Test | This test performs a sequential memory read/write by incrementing after every read/write | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary •Select test 3 in menu and check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
4 |  | CSK_SW_DIAG_TEST_004 | Complete Memory Read/Write test | This test performs a memory read/write for the whole DDR memory | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary •Select test 4 in menu and check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
5 | HDMI | CSK_SW_DIAG_TEST_005 | Color bar pattern test | This test displays a color bar on the HDMI Display device | • Connect target in CCS • Run the GEL file scripts according to readme • Check the color bar pattern on HDMI display |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
6 | TVOUT | CSK_SW_DIAG_TEST_006 |  |  |  |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
7 | LED | CSK_SW_DIAG_TEST_007 | LED toggle test | This test toggles the LED's in a pattern | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary • Check the LED's to toggle in a pattern |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
8 | NAND | CSK_SW_DIAG_TEST_008 | Read/write test | This test performs a read/write for first 4 blocks of device | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
9 | SD CARD | CSK_SW_DIAG_TEST_009 | Card detect test | This test whether an sd card is inserted in the slot or not | • Insert an SD card on J14 connector • Connect the target and Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
10 |  | CSK_SW_DIAG_TEST_010 | Read/write test | This test performs a read/write test on sd card | • Insert an SD card on J14 connector • Connect the target and Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
11 | USB | CSK_SW_DIAG_TEST_011 | Read/write test | This test performs a read/write test on sd card | • Insert an SD card on J14 connector • Connect the target and Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
12 |  | CSK_SW_DIAG_TEST_012 | Device information test | The test checks the device Manufacturer name, Vendor ID, Product ID, device class and the device speed/VBUS levels | • Connect a USB device on J12 connector • Connect the target and Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
13 | BLUETOOTH | CSK_SW_DIAG_TEST_013 | Device detect test | This test performs a device detect test to check if it is a TI BT chip by reading it's manufacturing ID | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
14 | AUDIO | CSK_SW_DIAG_TEST_014 | Audio codec test | This test configures the McASP1 on the DM388 board and AIC3104 on carrier card for record from Line-In and playback on Line-out | • Connect the head-phone to board at LINE OUT port • Connect the audio input to LINE IN port • Connect target in CCS • Run the GEL file scripts according to readme • Start playing audio on the device connected in LINE IN • Load & run the binary and observe Line-In input being played out of the head-phone for 20 seconds |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
15 | ETHERNET | CSK_SW_DIAG_TEST_015 | GMII internal PHY loopback tes | This test performs an GMII internal PHY loopback and verifies received packets | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
16 |  | CSK_SW_DIAG_TEST_016 | MII external cable loopback test | This test performs an MII external cable loopback and verifies received packets | • Connect a loopback cable on RJ45 connector • Connect the target and Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
17 | UART | CSK_SW_DIAG_TEST_017 | UART loopback test | This test validates the UART-0 Port on the board for its connectivity | • Connect target in CCS • Run the GEL file scripts according to readme • Setup a serial console with below configurations BaudRate - 115200 Data - 8bit Parity - None Stop Bits - 1 Flow Control - None • Load & run the binary • Check the messages displayed on the console • Enter 10 characters on the console and verify that data is received by the program and sent back to console properly |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
18 | CAMERA | CSK_SW_DIAG_TEST_018 | Camera GPIO toggling | This test performs all data,HS,VS and PCLK to act as GPIO's toggling | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary •Probe the data lines,HS,VS and PCLK and confirm the lines are toggling |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
19 | WLAN | CSK_SW_DIAG_TEST_019 | Device detect test | This test performs a device detect test to check if it is a WL1837 chip by reading it's manufacturing ID | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary • Check the test results on CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | OK
20 | SWITCHES | CSK_SW_DIAG_TEST_020 | Switch Push button test | This test performs the pushbutton test on the switches | • Connect target in CCS • Run the GEL file scripts according to readme • Load & run the binary • Press the switches and confirm the result in CCS console |  | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS