## Design Notice--REVA
Design Error check

## Design Error
| Related Board | Issue/Problem | workaround | action | Status
1 | MainBoard | U12 has wrong block (should be 9 Pin out but REVA is 6 Pin | interposer card for U12(TPS62901RPJR) | needs to be have a right block for TPS62901 in next version | Changed to TPSM861252 in Rev B
2 | MainBoard | Copper cylinder from Main to GF was no gap on PCB hole | shrink the diameter a bit from 3mm to 2.8mm | Add to 3.2 hole size there | Workaround Solution Ongoing
3 | MainBoard | PCB(Main) has failed on REVA, 3/5 failure on fabrication | Eagle has sent 5 PCS good boards to Dallas | Ask Eagle to add pp thickness, which is too thin at the beginning, | Eagle improve
4 | Other | Test Fixture for 12V not 54V | Check with customer for 54V fixture or fixture gerber | Have own desgin fixture on next build | Not for now
5 | MainBoard | Output choke L7 need additional copper plat to connect main | addional copper plat by manual | Have right spec on L7 to fit main board | Changed in Rev B
6 | MainBoard | Fuse shortage on assembly | find the same spec on digikey for assembly | Not a follow action, Just need to make sure the part has stock on next build | Workaround Solution Ongoing
7 | D2D Board (Module version) | 2 pcs Resonant Core assembly hard | maually enlarge the hole on the sheet 4 & sheet 5 | enlarge the hold for resonant core by adding 0.2mm rad on sheet4~5 | waiting for modification
8 | D2D Board & MainBoard (Module version) | Power Trace is difficult to fanout |  | better to swap the position of PGND with control signals | waiting for modification
9 | MainBoard | PFC GaN daughter card slot is rectanglar, need smaller angle. |  |  | waiting for modification
10 | MainBoard (Module version) | LLC module 二次側 Pin也插不進去,需要把主板洞削大一點才放得進去 | Maually enlarge the hole on mainboard | Enlarge mainboard hold to 3.2mm (both primary and secondary), change LLC winding board to 2.8mm thickness. | No need for Cyntec version
11 | MainBoard | PFC 子卡這兩個地方導角太圓,需要削掉一點子卡才插得進去 | same to item9?
12 | MainBoard (Module version) | DCDC module foot print don't have torlerance, need extend | Same to item 10
13 | MainBoard | PFC Daughter board is conflicted with CM Choke |  | GaN board shift up 0.5mm
14 | MainBoard | No Fan connector and LED connector
15 | GoldFinger | 需要露铜，且在厚度方向加倒角
16 | GoldFinger | Need to add 2.9mm height signal connector for Gold Finger
17 | Bias Flyback | Bias Flyback 的Connecter 都要DNP, 目前一個Connector母的在Bottom side.一個公的在Top side
18 | MainBoard | PFC stage need to support DC input, add a push-pull for highside bias of MOSFET leg.
19 | MainBoard | AuxP Pin7 should connect to VBB，not pGND. Up-down side has been flipped before fabrication. |  |  | fixed in Rev B
20 | MainBoard | Need temp sensor for inlet, out let, hotspot |  |  | waiting for later version to fix
21 | C2000 Board | Load sharing design need change to average + droop
22 | MainBoard | 5Vs is 3.3V now, R22 value is wrong. | R22 should be 73.2k |  | Changed to TPSM861252 in Rev B
23 | C2000 Board | SR2L need use GPIO10, with PWM6A. (new PWM is used in PMP41017 for 2ph IL) | short GPIO10/pin76 with GPIO9/pin75 | Change firmware to use PWM5B, GPIO9
24 | MainBoard | LLC Module primary side signal pin5 & Pin6 are swapped | cut board | swap the pin5a/b & pin6a/b | Changed with Cyntec transformer
25 | D2D Board | leakage inductance is too large (7uH) | enlarge the gap of Lr to 2.8mm
26 | D2D Board | sheet5 HS FET doesn't have open window for heatsink/copper | not need heatsink for now
27 | MainBoard | U15 needs Mark of Pin1 |  |  | Changed to TPSM861252 in Rev B
28 | D2D Board | sheet3 need to cut off more to avoid air gap. | Done, but still have issues.
29 | MainBoard | Change MV BUCK to the latest MODULE, TPSM861252. |  |  | Changed to TPSM861252 in Rev B
30 | D2D Board | HV GaN driver change to UCC21231
31 | C2000 Board | Fan connector location move to other location to avoid conflict
32 | MainBoard | Output choke conflict to LLC module, need to resolve in next version |  |  | Changed with Cyntec transformer
33 | MainBoard | Main board to Golden Finger connector(copper) need to find self design
34 | MainBoard | Main board to Golden Finger connector(signal) to search part for fit the dimension
35 | MainBoard | L1 part number need to be correct to PAL6598.223NL in Altium and issue the part in vault
36 | MainBoard | TTPL PFC Low Frequency SiFET hi-side Bias supply need to be a individual by push-pull.
37 | MainBoard | 12V to 5V buck IC change to TPSM863252、TPSM861252 | same to item 29 |  | same to item 29
38 | MainBoard | find WV Buck for Fan power, share with AuxPower |  | LM656xx-Q1 with 3.5A, https://www.ti.com/product/LM65645-Q1