## Sheet1
Proposal # | 82 |  |  |  | Project Manager |  | Art Kay (art_kay@ti.com)
I/O | 10038860 |  |  |  | DCC Deadline (samples) |  | 2013-01-31
Cost Center |  |  |  |  | Full documentation release |  | 2013-07-15
[5 empty] | TI RTM Deadline |  | 2013-08-15
Project Name | INA225EVM
This project can be started from the existing INA210EVM. This current shunt monitor will have pin straped gain values. It does not have a digital interface, so no software is required. It will be a analog PCB and schmatic design. Sample EVMs will be required before RTM.
Deliverables
1 | Schematic
2 | Test and Test Document for EVM
3 | Bill of materials
4 | Technical documentation (user's guide, test procedure)
Hourly Rate: | 60
| Development Hours |  |  |  | Fabrication Cost
Description | Hardware | Software | Testing | Documentation | Hardware Cost | Parts Cost | Build Cost | Extra Expenses | DCC Total | Project Total (+5%)
Original | 40 | 0 | 20 | 10 | 1000 | 1000 | 400 |  | 6600 | 6930
| Development Subtotal: |  |  | 4200 | Fabrication Subtotal: |  |  | 2400