## Changes made
SK-AM62P - Changes Required for REV E2 release
SK-AM62P Sub Section | Changes to be made on SK-AM62P SCH | Reason for changes | TI Comments | Status | Comments
USB Type A Connector | C625 has been added in the power pin of the ESD protection IC(U87) | A Decap has been added near to ESD protection IC as there is no decap present near to the IC |  | Closed
PD Controller | SoC_I2C0_SCL, SoC_I2C0_SDA and PD_I2C_IRQ was swapped from I2C2 port of the PD controller(U103) to I2C1 port | I2C port of the PD controller has been swapped since there is an I2C address conflict occuring with the External DSI LCD |  | Closed
VDDA_1V8 | Oscillator(U7) and clock buffer(U8) has been powered up from VDDA_1V8 to VDDA1V8 | VDDA1V8 is given to the Oscillator(U7) and clock buffer(U8) as only SOC needs to get monitored by the Current monitoring IC |  | Closed
Ethernet PHY1 | R114 and R116 which is present near to the Ethernet PHY1 (U77)has been replaced 0E to 100E | After replacing from 0E to 100E,rise time of the clock and data of the Management bus of the Ethernet PHY got increased so that latching of clock and data is consistent.Because of this change the inconsistent issue got eliminated. |  | Closed
PD Controller | Load switch(U134) and its corresponding components were added at the output side of the PD controller(U103) | Load switch implementation is done inorder to sense the external supply to get powered on when the rated sourcing powering of external supply is 15W at 5V and 12V. |  | Closed
USB Type A Connector | Pulldown resistor(R169) present in the load switch(U28) has been made as DNI | This is required by USB wakeup from deepsleep, as DRVVBUS has an internal pulldown during reset. |  | Closed
SOC Clock | R39 and C12 which is present near the R38.2 needs to be removed | Implemented based on TI comments |  | Closed
SD card interface | C276 has been changed from 1uF to 4.7uF and C273 has been changed from 4.7uF to 1uF | Input and Output capacitors of the load switch was changed based on the datasheet recommendation |  | Closed
GPMC | Place R409 near to the SOC | Implemented based on TI comments |  | Closed
SPI | Series resistor(R652) has been added in the EXP_SPI0_CLK net | Implemented based on TI comments |  | Closed
Mcasp | Series resistor(R133) has been updated from 0E to 22E in the AUDIO_EXT_REFCLK1 net. | Implemented based on TI comments |  | Closed
SPI | Series resistor(R653) has been added in the SOC_SPI2_CLK net | Implemented based on TI comments |  | Closed
Wakeup domain clock | C40 and C43 values has been updated from 12pF to 18pF | Load capacitors values of the Crystal Oscillator(Y1) were changed based on the SOC datasheet recommendation |  | Closed
VMON_SYS | VMON_SYS resistor (R59) value changed from 51K to 51.7 |  |  | Closed
SOC and PMIC | SOC and PMIC Manufacturing part number needs to be updated | The symbol names and part number to match the datasheet | Update SoC part number as AM62P54CVMSIAMHRQ1 for E2 revision | Closed
User expansion connector | C180 from Load switch(U50) and C178 from Load switch(U48) needs to be changed from 1uF to 0.1uF | Input and Output capacitors of the load switch was changed based on the datasheet recommendation |  | Closed
Reset | R528 has been updated from 10K to 47K | VIL actual voltage level of the signal GPIO1_23_INTn is closer to the VIL maximum of the SOC |  | Closed
MCU | Series resistor(R643) has been updated from 0E to 22E in the MCU_SPI0_CLK net | Implemented based on TI comments |  | Closed
SoC Reset | RC circuit (R654 and C577) has been added in the PMIC_INT signal | Implemented based on TI comments |  | Closed
GPMC | Series resistor(R655) has been added in the MCASP1_ACLKX net | Implemented based on TI comments |  | Closed
SOC Power | FL10 has been removed and VDD_MMC0 is directly shorted with VDDR_CORE | Shorting VDDR_CORE with VDD_MMC0 rail improves the PDN performance of VDD_MMC0 which is related to the eMMC |  | Closed
SOC Power | FL7 has been removed and VDDA_DLL_MMC0 net is shorted with VDDR_CORE | Implemented based on TI comments |  | Closed
SOC Power | C579 and C580 decaps (0.1uF) have been added to SoC_DVDD1V8 rail | Implemented based on TI comments |  | Closed
SOC Power | C566, C269 and C46 have been DNI'd | Implemented based on TI comments |  | Closed